## IT Portfolio Status Report
IT PORTFOLIO STATUS REPORT TEMPLATE
FOR PROJECT PERIOD STARTING
Monday, May 5th
THROUGH
Tuesday, February 10th
LIVE PROJECTS TIMELINE
| TIMELINE |  |  |  | PROJECT NOTES
PROJECT TITLE | START DATE | END DATE | DURATION in days | STATUS | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
Project A | 2025-05-05 | 2025-07-01 | 58 | Proposed | [6 empty] | STATUS KEY
Project B | 2025-05-10 | 2025-08-10 | 93 | In Progress | [6 empty] | Proposed
Project C | 2025-06-10 | 2026-02-01 | 237 | Complete | [6 empty] | In Progress
Project D | 2025-06-22 | 2025-08-04 | 44 | On Hold | [6 empty] | Complete
Project E | 2025-07-14 | 2025-11-01 | 111 | Overdue | [6 empty] | On Hold
Project F | 2025-07-14 | 2026-01-20 | 191 | Needs Review | [6 empty] | Overdue
Project G | 2025-08-01 | 2025-10-01 | 62 | Scheduled | [6 empty] | Needs Review
Project H | 2025-08-14 | 2025-08-30 | 17 | [7 empty] | Scheduled
Project I | 2025-09-01 | 2025-12-10 | 101
Project J | 2025-10-01 | 2025-11-15 | 46
Project K | 2025-10-01 | 2025-12-01 | 62
Project L | 2025-11-01 | 2025-12-01 | 31
Project M | 2025-11-10 | 2025-12-10 | 31
Project N | 2025-12-01 | 2026-02-10 | 72
IT PORTFOLIO TIMELINE
PLANNED PROJECTS TIMELINE
PROJECT TITLE | PLANNED START DATE | PLANNED ENDING DATE | DURATION in days | STATUS | PERCENT COMPLETE | RISKS/CONCERNS
Project A | 2025-05-05 | 2025-07-01 | 58 | Proposed | 0% | [5 empty] | STATUS KEY
Project B | 2025-05-10 | 2025-08-10 | 93 | In Progress | 50% | [5 empty] | Proposed
Project C | 2025-06-10 | 2026-03-01 | 265 | Complete | 100% | [5 empty] | In Progress
Project D | 2025-06-22 | 2025-08-04 | 44 | On Hold | 24% | [5 empty] | Complete
Project E | 2025-07-14 | 2025-11-01 | 111 | Overdue | 10% | [5 empty] | On Hold
Project F | 2025-07-14 | 2026-01-20 | 191 | Needs Review | 95% | [5 empty] | Overdue
Project G | 2025-08-01 | 2025-10-01 | 62 | Scheduled | 0% | [5 empty] | Needs Review
Project H | 2025-08-14 | 2025-08-30 | 17 | [7 empty] | Scheduled
Project I | 2025-09-01 | 2025-12-10 | 101
Project J | 2025-10-01 | 2025-11-15 | 46
Project K | 2025-10-01 | 2025-12-01 | 62
Project L | 2025-11-01 | 2025-12-01 | 31
Project M | 2025-11-10 | 2025-12-10 | 31
Project N | 2025-12-01 | 2026-02-10 | 72
PROJECT FINANCIAL STATUS
PROJECT TITLE | BUDGETED COSTS | ACTUAL COSTS | FORECAST | VARIANCE
Project A | 4500 | 5000 | 5000 | -500
Project B | 5000 | 6500 | 4500 | -1500
Project C | 2600 | 1700 | 2300 | 900
Project D | 4300 | 4000 | 6000 | 300
Project E | 8500 | 9750 | 10000 | -1250
Project F | 18750 | 17000 | 18500 | 1750
Project G | 15000 | 14985 | 16000 | 15
Project H | 26000 | 28000 | 30000 | -2000
Project I | 3900 | 4500 | 4000 | -600
Project J | 2750 | 3000 | 3000 | -250
Project K | 25600 | 29500 | 30000 | -3900
Project L | 6700 | 6000 | 7000 | 700
Project M | 29000 | 32000 | 30000 | -3000
Project N | 48000 | 35000 | 45000 | 13000
TOTALS | 200600 | 196935 | 211300 | 3665
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - IT Portfolio Status Rpt
IT PORTFOLIO STATUS REPORT TEMPLATE
FOR PROJECT PERIOD STARTING
THROUGH
LIVE PROJECTS TIMELINE
| TIMELINE |  |  |  | PROJECT NOTES
PROJECT TITLE | START DATE | END DATE | DURATION in days | STATUS | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
Project A |  |  | 1 | [7 empty] | STATUS KEY
Project B |  |  | 1 | [7 empty] | Proposed
Project C |  |  | 1 | [7 empty] | In Progress
Project D |  |  | 1 | [7 empty] | Complete
Project E |  |  | 1 | [7 empty] | On Hold
Project F |  |  | 1 | [7 empty] | Overdue
Project G |  |  | 1 | [7 empty] | Needs Review
Project H |  |  | 1 | [7 empty] | Scheduled
Project I |  |  | 1
Project J |  |  | 1
Project K |  |  | 1
Project L |  |  | 1
Project M |  |  | 1
Project N |  |  | 1
IT PORTFOLIO TIMELINE
PLANNED PROJECTS TIMELINE
PROJECT TITLE | PLANNED START DATE | PLANNED ENDING DATE | DURATION in days | STATUS | PERCENT COMPLETE | RISKS/CONCERNS
Project A |  |  | 1 | [7 empty] | STATUS KEY
Project B |  |  | 1 | [7 empty] | Proposed
Project C |  |  | 1 | [7 empty] | In Progress
Project D |  |  | 1 | [7 empty] | Complete
Project E |  |  | 1 | [7 empty] | On Hold
Project F |  |  | 1 | [7 empty] | Overdue
Project G |  |  | 1 | [7 empty] | Needs Review
Project H |  |  | 1 | [7 empty] | Scheduled
Project I |  |  | 1
Project J |  |  | 1
Project K |  |  | 1
Project L |  |  | 1
Project M |  |  | 1
Project N |  |  | 1
PROJECT FINANCIAL STATUS
PROJECT TITLE | BUDGETED COSTS | ACTUAL COSTS | FORECAST | VARIANCE
Project A |  |  |  | 0
Project B |  |  |  | 0
Project C |  |  |  | 0
Project D |  |  |  | 0
Project E |  |  |  | 0
Project F |  |  |  | 0
Project G |  |  |  | 0
Project H |  |  |  | 0
Project I |  |  |  | 0
Project J |  |  |  | 0
Project K |  |  |  | 0
Project L |  |  |  | 0
Project M |  |  |  | 0
Project N |  |  |  | 0
TOTALS | 0 | 0 | 0 | 0
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.