## EXAMPLE Project Resources
Project Resource Allocation Tracking Template Example
auto-calculates
Resource | Name | Status | Start Date | End Date | Duration in Days | Comments
Project Manager | Makara McLean | In Progress | 2024-01-02 | 2024-01-11 | 10
Designer | Makara McLean | On Hold | 2024-01-07 | 2024-01-11 | 5
Quality Assurance | Krisa Ahmed | In Progress | 2024-01-10 | 2024-02-23 | 45
Business Analyst | Krisa Ahmed | In Progress | 2024-01-10 | 2024-01-20 | 11
Marketing Manager | Karl Peter | Complete | 2024-01-16 | 2024-01-29 | 14
Software Developer | Karl Peter | In Progress | 2024-01-19 | 2024-02-01 | 14
Tester | Brennan Gardiner | Complete | 2024-01-22 | 2024-02-09 | 19
Database Administrator | Aila Kishimoto | Not Started | 2024-01-28 | 2024-02-14 | 18
Health and Safety Professional | Brennan Gardiner | Not Started | 2024-01-28 | 2024-02-06 | 10
Resource Name | Makara McLean | Not Started | 2024-01-31 | 2024-02-02 | 3
Resource Name | Krisa Ahmed | Not Started | 2024-02-04 | 2024-02-12 | 9
Resource Name | Krisa Ahmed | Not Started | 2024-02-06 | 2024-02-14 | 9
Resource Name |  | In Progress | 2024-02-18 | 2024-03-26 | 38
Resource Name |  | Complete | 2024-02-18 | 2024-02-20 | 3
Resource Name |  | Complete | 2024-02-18 | 2024-02-23 | 6
Resource Name |  | On Hold | 2024-02-18 | 2024-02-26 | 9
Resource Name |  | In Progress | 2024-02-21 | 2024-02-23 | 3
Resource Name |  | In Progress | 2024-02-22 | 2024-02-23 | 2
Resource Name |  | In Progress | 2024-02-25 | 2024-03-26 | 31
Resource Name |  | On Hold | 2024-02-25 | 2024-03-26 | 31
Resource Name |  | Not Started | 2024-02-25 | 2024-02-28 | 4
Resource Name |  | In Progress | 2024-02-26 | 2024-03-03 | 7
Resource Name |  | In Progress | 2024-02-25 | 2024-03-06 | 11
Resource Name |  | In Progress | 2024-03-03 | 2024-03-26 | 24
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Project Resources
Project Resource Allocation Tracking Template
auto-calculates
Resource | Name | Status | Start Date | End Date | Duration in Days | Comments
|  | In Progress | 2024-01-02 | 2024-01-11 | 10
|  | On Hold | 2024-01-07 | 2024-01-11 | 5
|  | In Progress | 2024-01-10 | 2024-02-23 | 45
|  | In Progress | 2024-01-10 | 2024-01-20 | 11
|  | Complete | 2024-01-16 | 2024-01-29 | 14
|  | In Progress | 2024-01-19 | 2024-02-01 | 14
|  | Complete | 2024-01-22 | 2024-02-09 | 19
|  | Not Started | 2024-01-28 | 2024-02-14 | 18
|  | Not Started | 2024-01-28 | 2024-02-06 | 10
|  | Not Started | 2024-01-31 | 2024-02-02 | 3
|  | Not Started | 2024-02-04 | 2024-02-12 | 9
|  | Not Started | 2024-02-06 | 2024-02-14 | 9
|  | In Progress | 2024-02-18 | 2024-03-26 | 38
|  | Complete | 2024-02-18 | 2024-02-20 | 3
|  | Complete | 2024-02-18 | 2024-02-23 | 6
|  | On Hold | 2024-02-18 | 2024-02-26 | 9
|  | In Progress | 2024-02-21 | 2024-02-23 | 3
|  | In Progress | 2024-02-22 | 2024-02-23 | 2
|  | In Progress | 2024-02-25 | 2024-03-26 | 31
|  | On Hold | 2024-02-25 | 2024-03-26 | 31
|  | Not Started | 2024-02-25 | 2024-02-28 | 4
|  | In Progress | 2024-02-26 | 2024-03-03 | 7
|  | In Progress | 2024-02-25 | 2024-03-06 | 11
|  | In Progress | 2024-03-03 | 2024-03-26 | 24
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - DO NOT DELETE
DROPDOWN KEYS - Do Not Delete
Status
Not Started
In Progress
Complete
On Hold

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.