## EXAMPLE Goal Setting Plan
Goal Setting Plan Template Example
Project Name | Event ABC
Project Manager | Anthony G.
Action | Responsible | Priority | Potential Obstacles | Potential Solutions | Start | End | Notes
Goal #1: Select Venue
Identify venue options | Sally J. | High | Limited venue availability on preferred dates | Expand date range; consider weekday options | MM/DD | MM/DD
Visit venues | Sally J. | Medium | Scheduling conflicts with venue managers | Schedule visits in advance; confirm 24 hours prior | MM/DD | MM/DD | Must send contracts by 10/10
Sign contract | Maria S. | Low |  |  | MM/DD | MM/DD
[5 empty] | MM/DD | MM/DD
Goal #2: Secure Speakers
Recruit speakers | Sally J. | High | Limited speaker availability | Reach out early and contact backup speakers | MM/DD | MM/DD
Speaker bios | Sally J. | Medium | Delays in receiving bios from speakers | Set a deadline; send reminders a week in advance | MM/DD | MM/DD
Create and send speaker packets | Maria S. | Medium | Design and printing delays | Use templated packet design and a digital version | MM/DD | MM/DD | Send to stakeholders
Confirm speakers | Sally J. | High |  |  | MM/DD | MM/DD
[5 empty] | MM/DD | MM/DD
Goal #3: Recruit Sponsors
Identify sponsors | John S. | High | Cold leads and slow responses | Use warm introductions; prioritize high-probability leads | MM/DD | MM/DD
Write up sponsor agreement | Maria S. | Medium | Legal language confusion | Use a pre-approved template from legal team | MM/DD | MM/DD
Send emails | John S. | High | Low open or response rates | Personalize emails and A/B test subject lines | MM/DD | MM/DD
Make cold calls | John S. | Medium | Not started |  | MM/DD | MM/DD | From the sales team
[5 empty] | MM/DD | MM/DD
Goal #4: Promote event
Create banners | Morgan K. | Low | Delays from vendor | Identify multiple banner vendors as backups | MM/DD | MM/DD
Order swag | Morgan K. | Low |  |  | MM/DD | MM/DD | Coffee mugs, totes, pencils
Create social media strategy | Corrine J. | Low | Lack of clear messaging | Hold a kickoff meeting with key stakeholders for alignment | MM/DD | MM/DD
Make marketing materials | Karen Z. | Low | Inconsistent branding | Use approved brand guide; get early sign-off from marketing lead | MM/DD | MM/DD
[5 empty] | MM/DD | MM/DD
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Goal Setting Plan
Goal Setting Plan Template
Project Name
Project Manager
Action | Responsible | Priority | Potential Obstacles | Potential Solutions | Start | End | Notes
Goal #1:
Goal #2:
Goal #3:
Goal #4:

## Priority Key - Do Not Delete
Priority Key - Do Not Delete
High
Medium
Low

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.